## Project Plan
Project plan detail
Marketing Plan Lists |  |  |  | BRAG Status & Toggle
|  |  |  | Not Started | In Progress | Delayed | Complete | Add your own status | No Status
|  |  |  | ON | ON | ON | OFF | OFF | ON
Task | Task Summary | Status | Team | Owner | Assigned to | Anticipated Start Date | Anticipated End Date | Actual Start Date | Actual End Date | Estimated Cost | Actual Cost
Task 1 |  | Not Started | Team C | AA | DD | 2026-07-01 | 2026-08-01 | 2026-06-28 |  | 1500 | 1250
Task 2 |  | In Progress | Team F | BB | CC | 2026-07-15 | 2026-08-15 | 2026-07-13 |  | 2000 | 1840
Task 3 |  | Delayed | Team E | CC | DD | 2026-08-01 | 2026-08-20 |  |  | 1450
Task 4 |  | Complete | Marketing | DD | EE | 2026-06-01 | 2026-07-01 | 2026-06-01 | 2026-06-28 | 3000 | 3200
Task 5 |  | No Status | Team A | EE | FF | 2026-09-01 | 2026-09-15 |  |  | 500
Task 6 |  | No Status | Team C | FF | CC |  |  |  |  | 575 | 125
Task 7 |  | No Status | Team F | GG | CC | 2026-09-12 | 2026-09-25 |  |  | 1750
Task 8 |  | No Status | Team C | HH | EE | 2026-07-01 | 2026-10-01 | 2026-07-01 |  | 925 | 250
Task 9 |  | No Status | Team F | CC | GG | 2026-07-15 | 2026-08-15 | 2026-07-13 |  | 2000 | 1840
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15
[10 empty] | 13700 | 8505
Go to Plan Lists

## RACI
RACI summary
Task | Marketing Director | Role 2 | Role 3 | Role 4 | Role 5 | Role 6 | Role 7
Task 1 | C | bar: Role 2 to Role 7
Task 2 | R | R | R | A | C | I | R
Task 3 | A | bar: Role 2 to Role 7
Task 4 | R | bar: Role 2 to Role 7
Task 5 | A | bar: Role 2 to Role 7
Task 6 | C | bar: Role 2 to Role 7
Task 7 | I | bar: Role 2 to Role 7
Task 8 | C | bar: Role 2 to Role 7
Task 9 | C | bar: Role 2 to Role 7
Task 10 | C | bar: Role 2 to Role 7
Task 11 | C | bar: Role 2 to Role 7

## Instructions & List Data
Project Plan lists
Table 1 |  |  | Table 2
Name | Title |  | Department | 1. Add the names of your project team and their role titles into Table 1
AA | Marketing Director |  | Team A | 2 Add the list of departments involved in the project to Table 2
BB | Role 2 |  | Team B | 3. Start to build up the Project plan and select the team members and Departments from the drop down lists.
CC | Role 3 |  | Marketing | 4. Select the status of the action from the list. You can turn off any status from the list using row 4 in the project plan
DD | Role 4 |  | Team D | 5. Move onto the RACI sheet and allocate the role status to the tasks, from the summary in Table 3
EE | Role 5 |  | Team E
FF | Role 6 |  | Team F
GG | Role 7 |  | Team G
Table 3
Status | Action | Rating
Responsible | Does the work to complete the task. | R
Accountable | Delegates work and has sign off for tasks | A
Consulted | Provide input based on how it will impact their work or team | C
Informed | Need to be kept in the loop on progress | I